## Eval
TEAM TASK EVALUATION
Student Name:	Kadir Emre Oto
Student ID:	150140032
Team Name:	MerdoBot
Task:	Final report & demo

How well did your team work together on this task?	Very well
Estimate how many hours you spent on this task?	40
Estimate how many hours in total your team spent on this task?	100

Name 3 things the team did well together on this task:
1. Helping each other. / 2. We had fun when we run the whole program. / 3. Getting along well with each other.

Name 3 things the team did not do so well together:
1. Determining requirements. / 2. Dividing up major tasks (inefficient division). / 3. Leaving write-up to last moment.

Team member evaluations:
	Members:
Items:	Muhammed Burak Buğrul	Mertcan Yasakçı	Hüseyin Aküzüm	Pelin Hakverir	Mehmet Barış Yaman
Workload: / Took on a proportional amount of work in the task.	Adequate	Adequate	Adequate	Adequate	Adequate
Dependability: / In a timely manner, finished & followed through on tasks taken on.	Adequate	Adequate	Adequate	Adequate	Adequate
Process: / Facilitated communication & planning.	Adequate	Adequate	Adequate	Adequate	Adequate
Initiative: / Worked independently and generated ideas & directions.	Adequate	Adequate	Adequate	Adequate	Adequate

Suggest at least one thing that the team could do to improve its future performance:
Prepare the first draft well in advance and start reviewing it early (to account for team member schedules and likely revision). / Check projector with our computer and Ubuntu. Bring a mouse. Get all the necessary commands ready before the demo. / Give more importance for dividing up the tasks. Get more help may be a better idea.